## Sheet1
Project | TaskType | IT Issues / Changes / Additions | Reported Date | EDD | Actual Delivery Date | Status | Type | Reason for pending and hold
Performics Manager | App | Allow numbers only in numeric inputs and decimals only in Decimal type inputs | 2022-10-19 | 2022-10-19 | 2022-10-19 | Done
Performics Manager | App | Add Noticeboard Section1 part | 2022-10-19 | 2022-10-20 | 2022-10-26 | Done
Test | App | Maps- show geotag screen and show marked location on map | 2022-10-19 | 2022-10-20 | 2022-10-20 | Done
Test | App | WaterMark on images | 2022-10-19 | 2022-10-20 | 2022-10-26 | Done
One App | Portal | Redesign pages in react js | 2022-10-13 | 2022-10-14 | 2022-10-14 | Done
Horlicks | Detailer App | Make new react nativce static detailer app - design Framework | 2022-10-14 | 2022-10-18 | 2022-10-19 | Done